## Sheet1
|  |  | Roles: Administrators, Clients, Visitors, Companies |  | Rank of priority: 1- critical 2- important 3- medium 4- low
New Assignment | ID | STORY / FEATURE / REQUEST | Dependency | Story Points | Priority | Status | Success Demos | Failure Demos | Notes
Nader | a.a | As an Administrator, I can answer questions asked by users so that it can be viewed by other users. |  |  | Medium | Done | 1. Clients ask questions 2.The administrator should be able to answer the questions asked by the clients concerning technical issues. | none
| a.b | As an Administrator, I can delete reviews so that I can maintain a clean environment. |  |  | LOW | Unapproached | Administrator is able to delete inappropriate reviews written by users. | none
Mahmoud | a.c | As an Administrator, I can interact with companies so that I can accept them. |  |  | CRITICAL | Done | 1.company requests for subscription 2.Admin verifies request for subscription and contacts company for further contract details. Then admin accepts the request. | Admin chooses not to accept subscription request
| a.d | As an Administrator, I can delete inactive users so that I can keep the environment updated. |  |  |  | Unapproached | Administrator is able to delete users who have been inactive for a specific period. | The client username does not match any username in the database
Mahmoud | a.e | As an Administrator, I can delete companies who are discontinued, unsubscribed, or failed to pay so that I can keep the environment updated. |  |  | Medium | Done | 1.discontinuation of the business or the user provider fails to pay or decides not to continue with the subscription. 2.Administrator chooses to delete a company | none
Mahmoud |  | As an administrator, I can register so that I ca ncreate an account |  |  | CRITICAL | Done | 1.A logged in admin chooses the registration option. Logged in admin fills information about the other admin; questions | 1.Admin leaves a mandatory field empty 2. Admin uses an already taken username.
Mahmoud |  | As an administrator, I can login so that I can access my account |  |  | CRITICAL | Done | 1.Admin chooses the login option. 2. He is then prompted to fill in his username (mandatory), password (mandatory) and presses login | 1- Admin does not provide username or password. 2- Password does not match provided username, a relevant error message is displayed 3-Login is unsuccessful
Syrine |  | As an administrator, I can logout so that I can leave the website |  |  | CRITICAL | Done | 1.Admint chooses the logout option. 2. Admin isthen directed to the home page. | none
Rokaya | b.a | As a company, I can subscribe so that I can create an account |  |  | CRITICAL | Done | 1.company chooses the subscription. Student is then prompted to fill in his 2.company presses subscribe. 3.company is registered to the system and his or her record is added to the database accordingly, to be verified by the system administrator | 1.company does not provide any of the mandatory data.2. Username already exists, a relevant error message Is displayed.3.Password does not meet the above listed requirements, a relevant error message is displayed.
Rokaya | b.b | As a company, I can login so that I can view my profile |  |  | CRITICAL | Done | 1.company or client chooses the login option. 2.He is then prompted to fill in his username (mandatory), password (mandatory) and presses login | 1.company or client does not provide username or password. 2. Password does not match provided username, a relevant error message is displayed. Login is unsuccessful
Syrine | b.c | As a company, i can logout so that i can leave the website |  |  | LOW | Done | 1.company or client chooses the logout option. 2.company or client is then directed to the home page. | none
Rokaya | b.d | As a company, I can create an event so that it can be viewed |  |  | CRITICAL | Done | 1.company chooses the add event option. 2. He is then prompted to fill in the event name, date, duration, location, details about event, contacts for further details on event, and assign a picture for the event. 3.company is prompted with a confirmation message that the event has been created and available to users for booking | 1.company does not provide any of the mandatory data. 2.Event date has already passed.
Daniel | b.e | As a company, i can view my events so that i can track which events are online. |  |  | IMPORTANT | Done | 1.company chooses the view my events option. 2.He can then view a list of the events created by him, as well as the number of bookings made to the event. | No events are available. An appropriate message is displayed
| b.f | As a service provider, i can view my services so that i can track which services are online |  |  | IMPORTANT | Done | Service provider chooses his company from company list and is directed to the company profile and the services offered are displayed | none
Ali | b.g | As a company, I can create services so that it can be viewed |  |  | CRITICAL | Done | 1.company chooses to add a service to his catalogue of products. 2. He is then prompted to fill in the service name, availability, duration, description of service, price, and assign a picture to the service. All mentioned information is mandatory. 3.company is prompted with a confirmation message that the service has been successfully added to his catalogue and is available to users for reservation. | company does not provide any of the mandatory data
Ali | b.h | As a company, I can update my services so that I can keep users up to date. |  |  | MEDIUM | Done | 1.company chooses to update a service in his catalogue of offered services.2. He is then prompted to fill in the information to be updated including: service name, availability, duration, description of service, price, and picture and save changes 3. company is prompted with a confirmation message that the service has been successfully updated in the catalogue. | company does not fill in any information to be updated; a relevant error message is displayed.
Ali | b.i | As a company, I can delete my services that are no longer available. |  |  | MEDIUM | Done | 1.company chooses to delete a service in his catalogue of offered services. 2.He is then asked if he is sure he wants to delete service and can answer yes or no.3.company is prompted with a confirmation message that the service has been successfully deleted from the catalogue | company chooses no from message displayed on pressing delete.
Daniel | b.j | As a company, I can update my events so that I can keep users up to date |  |  | MEDIUM | Done | 1.company can choose to update event name, date, duration, location, details about event, contacts for further details on event, and picture for the event and saves the changes 2. The event is updated on the profile of the company | company does not fill in any information to be updated; a relevant error message is displayed.
Mireille | b.k | As a company, I can cancel my events |  |  | MEDIUM | Done | 1.company chooses the cancel event option. 2. Message displayed that the event has been successfully cancelled | none
Nader | b.l | As a company, I can view the rates and reviews of any user |  |  |  | Done | 1.Service Provider chooses the view my ratings and reviews option, and his ratings and reviews are then displayed. 2.Service Provider is redirected to a page with all the ratings and reviews on his profile. | none
Syrine | b.m | As a company, I can reset my password so that if I forget it |  |  | MEDIUM | Done | 1. a company chooses the login option. He then clicks on the “forgot password” option where he’d be asked to fill in his username. 2.Based on the username, he’d answer the security question he’d answered before while registering. 3.He is then directed to a page where he’d fill in the new password, and then presses change | 1. A client or a company does not provide username or answer. 2.A client or a company enters a wrong username, a relevant error message is displayed. 3. A client or a company enters a wrong answer to the security question, a relevant error message is displayed
Syrine | b.n | As a company, I can change my password so that I can update it. |  |  | LOW | Done | 1.A client or a company goes to settings. 2. He then clicks on the “change password” option where he’d be asked to fill in his old and new password, and then presses change | 1. A client or a company does not provide old password 2. A client or a company enter a wrong old password, a relevant error message is displayed
Shady | b.o | As a company, I can post promotions so that I can attract users. |  |  | IMPORTANT | Done | 1.company can post any promotion they have. 2. the company should fill in the period of promotion and if there’s any conditions in order to get the promotion. | Required fields is empty. e.g: period of the promotion. An appropriate message is displayed
Shady | b.p | As a company, I want to view my promotions so that I can see all my promotions |  |  | MEDIUM | Done | 1.company chooses the view his promotions option and is redirected to the page having the promotions offered by his company | No promotions are available. An appropriate message is displayed
Shady | b.q | As a company, I can update my promotions so that I can keep users updated |  |  | MEDIUM | Done | 1.company can update a promotion if they needs to by clicking on update promotion and change any data they have provided before about the promotion | Required fields are empty. e.g: period of the promotion. An appropriate message is displayed
Shady | b.r | As a company, I can delete my promotions so that I can remove expired promotions. |  |  | MEDIUM | Done | 1.company chooses to delete a promotion that he offered. 2.company is then prompted with a confirmation message that the promotion has been successfully deleted | none
| b.s | As a service provider, i can view my bookings so that i can keep track of the booking limit. |  |  | LOW | Unapproached (because the limit is settled from the beginning so not needed anymore) | 1.The service provider should be able to view all booked events, services or promotions he/she is offering. 3.list of bookings is retrieved and displayed | No bookings are available . An appropriate message is displayed
Nardine | c.a | as a visitor, I can view the profile of any company. |  |  | IMPORTANT | Done | 1. Vistor chooses to view a companies profile. 2. Visitor will be redirected to the another page where he or she can easily navigate through the website to see companies profiles’ with their names, city, area, category, branches, company logo,email, address, phone number, social media link, and ratings and reviews. | No companies exist. An appropriate message is displayed
Daniel | c.b | As a visitor, I can view the rates and reviews of any user. |  |  | MEDIUM | Done | 1. Visitor chooses to view the rates and reviews of a certain company. 2.Visitor will be redirected to be able to view other clients’ ratings and reviews for other businesses. This will include filters by highest/lowest ratings. | company doesn’t have any ratings or reviews yet
Syrine | c.c | As a visitor, I can view the promotions of any company. |  |  | IMPORTANT | Done | 1. Visitor chooses the view promotions option. 2. Visitor is directed to the page having promotions offered by all companies. | none
Sondos | c.d | As a visitor, I can view the events of any company. |  |  | IMPORTANT | Done | 1. Visitor chooses to the view events option. 2. The vistor will then be able to view the event name, date, location, price, host, and description. | No upcoming events. An appropriate message is displayed
Sondos | c.e | As a visitor, I can view the services of any company. |  |  | IMPORTANT | Done | 1. Visitor chooses the view services option. 2. Visitor chooses a company and is directed to the company profile and the services offered are displayed | none
Ali and Daniel | c.f | As a visitor, I want to search for the services of any service provider by using filters to make it easier to reach. |  |  | MEDIUM | Done | 1. Visitor chooses to filter for services. 2. The visitor will be directed to a page where he/she can choose to filter for a service by filling in the event name, company name, date and/or location. | No services exist that fit the filters chosen.
(estimated to be accessible from profile) | c.g | As a visitor, I can see the contact information of the company so that I can contact him. |  |  | MEDIUM |  | 1. Visitor chooses to use the contact us option. 2. The visitor will be redirected to the company's information. | No contact details are available. An appropriate message is displayed.
Ali and Daniel | c.h | As a visitor, I want a filter or category option or name so that I can easily find a desired event. |  |  | MEDIUM | Done | 1. Visitor chooses to filter for events. 2. The visitor will be directed to a page where he/she can choose to filter for an event by filling in the event name, company name, date and/or location. | No events exist that fit the filters chosen.
Ali and Daniel | c.i | As a visitor, i want a filter or category option or name so that i can easily find a company. |  |  | MEDIUM | Done | 1.Visitor chooses to search for company names. 2.Visitor chooses to search by filling in the company name and/or category name as well as choose by filtering the companies by area and/or city and/or category. | No companies exist that fit the search/filter chosen. An appropriate message is displayed.
Mahmoud | c.j | As a visitor, I can view the questions of any users so it may solve my problem. |  |  | MEDIUM | Done | 1.visitor chooses the questions section. 2.The vistor will head to the questions section which includes several questions and answers regarding popular topics and concerns that may be raised from website users. | none
Nader | d.a | As a client, I can register so that I can create an account. |  |  | CRITICAL | Done | 1.The client chooses the registration option. 2.Client fills his information; username (mandatory), password (mandatory) , profile picture, contact information (i.e e-mail, phone number, address, personal link) and security questions | 1.Client leaves a mandatory field empty 2. Client uses an already taken username.
Rokaya | d.b | As a client, I can login so that I can access my account. |  |  | CRITICAL | Done | 1.client chooses the login option. 2. He is then prompted to fill in his username (mandatory), password (mandatory) and presses login | - Client does not provide username or password. - Password does not match provided username, a relevant error message is displayed. Login is unsuccessful
Syrine | d.c | As a client, i can logout so that i can leave the website. |  |  | LOW | Done | 1.client chooses the logout option. 2. client is then directed to the home page. | none
Mireille | d.d | As a client, i can view my profile so that i can view my information. |  |  | IMPORTANT | Done | 1.Client chooses the view my profile option. 2.Client will be able to view all his information. | none
| d.e | As client, I can cancel bookings so that I can have a refund |  |  |  | Unapproached | Client has the ability to cancel a booking that he previously made, before the day of the booking | - No username was provided - No event name was provided
Daniel | d.f | As a client, I can view the rates and reviews of any user. |  |  | IMPORTANT | Done | Client is able to view other clients’ ratings and reviews for other businesses. This will include filters by highest/lowest ratings. | company doesn’t have any ratings or reviews yet
Nader | d.g | As a client, I can rate and review any company so that I can inform other users. |  |  | IMPORTANT | Done | Client is able to post ratings and reviews to all companies that are subscribed to the platform for other clients and companies to see | Client leaves review text empty
Syrine | d.h | As a client, I can reset my password so that if I forget it. |  |  | IMPORTANT | Done | 1.A client chooses the login option. 2. He then clicks on the “forgot password” option where he’d be asked to fill in his username. 3.Based on the username, he’d answer the security question he’d answered before while registering. 4. He is then directed to a page where he’d fill in the new password, and then presses change. | - A client does not provide username or answer. - A client enters a wrong username, a relevant error message is displayed. - A client enters a wrong answer to the security question, a relevant error message is displayed
Syrine | d.i | As a client, I can change my password so that I can update it. |  |  | IMPORTANT | Done | 1.A client goes to settings. 2.He then clicks on the “change password” option where he’d be asked to fill in his old and new password, and then presses change. | - A client does not provide old password - A client enter a wrong old password, a relevant error message is displayed
Sondos | d.j | As a client, I can view the events of any company. |  |  | IMPORTANT | Done | client can easily search in the website to view events. Each event includes event name, date, location, price, host, and description | No upcoming events. An appropriate message is displayed
Nardine | d.k | As a client, I can view the profile of any company. |  |  | IMPORTANT | Done | A client can easily navigate through the website to see companies profiles’ with their names, city, area, category, branches, company logo, email, address, phone number, social media link, and ratings and reviews posted by the clients. | No companies exist. An appropriate message is displayed
Ali and Daniel | d.l | As a client, I want a filter or category option so that I can easily find a desired event |  |  | MEDIUM | Done | A client or a visitor chooses to filter for events by filling in the event name, company name, date and/or location | No events exist that fit the filters chosen.
Ali and Daniel | d.m | As a client, I want a filter or category option so that I can easily find a service provider. |  |  | MEDIUM | Done | A client chooses to search by filling in the company name and/or category name as well as choose by filtering the companies by area and/or city and/or category. | No companies exist that fit the search/filter chosen. An appropriate message is displayed.
Ali and Daniel | d.n | As a client, I want a filter or category option so that I can easily find services. |  |  | MEDIUM | Done | 1. Client chooses to filter for services. 2. The Client will be directed to a page where he/she can choose to filter for a service by filling in the event name, company name, date and/or location. | No services exist that fit the filters chosen.
Mahmoud | d.o | As a client, I can view the questions of any user. |  |  | IMPORTANT | Unfinished (done, but missing button! Accessible when logged out) | A visitor or client choose to view the frequently asked questions section , which includes several questions and answers regarding popular topics and concerns that may be raised from website users. | none
Nardine (estimated to be accessible from profile) | d.p | As a client, I can see the contact information of the company so that I can contact them. |  |  | IMPORTANT | Done | 1. Visitor chooses to use the contact us option. 2. The visitor will be redirected to the company's information. | No contact details are available. An appropriate message is displayed.
Nardine | d.q | As a client, I can post a questions so that the admin can reply to it. |  |  | IMPORTANT | Done | A client chooses to post a question regarding a concern arising from website functionalities or any other inquiries regarding bookings. | none
Mireille and Sondos | d.r | As a client I can add to my favorites so that I can easily access my favorite information |  |  | LOW | Done
Rokaya | d.s | As a client, I can pay for service so that I can reserve a place. |  |  | IMPORTANT | Done | Client selects from upcoming activities (events, promotions, services), selects the required criteria and press book or chooses a payment method and presses pay. | Client doesn’t provide mandatory information. Error message is displayed. Payment/Booking process unsuccessful.
Rokaya | d.t | As a client, I can view my previous booking history. |  |  | IMPORTANT | Done (past + future bookings) | 1.Client enters his profile 2.uses the view booking history option. 3. His booking history is displayed and it includes the name of the event, the company name, the price, the date. | No booking history is available. An appropriate message is displayed
Mireille | d.u | As a client, I can update my personal data so that I can keep it up to date. |  |  | IMPORTANT | Done | Client chooses the view profile option. Client is then prompted to edit his personal data and presses update. | Client didn’t provide mandatory information. Error message is displayed.
Rokaya | d.v | As a client, I can view my upcoming bookings so that i can keep updated. |  |  | IMPORTANT | Done (past + future bookings) | 1.client enters his profile 2.uses the upcoming bookings option. 3.his upcoming bookings are displayed | Client does not have upcoming bookings
| d.w | As a client I can view my wishlist so that I can interact with it |  |  | IMPORTANT | Unapproached | 1.Client chooses to view the wishlist. 2.Client is redirected to access the list of activities in the wish list. | No activity in the wish list, an appropriate message is displayed
Mireille and Rokaya | d.x | As a client I can add to my wishlist so that I can later view it |  |  | IMPORTANT | Unfinished. (backend done but not frontend) | Client select from upcoming event or services or promotions and add it to his wish list. | No activity in the wish list, an appropriate message is displayed
Syrine | d.y | As a client, I can view the promotions of any company. |  |  | IMPORTANT | Done | Visitor or client chooses promotions option and is directed to the page having promotions offered by all companies | none
Sondos |  | As a client, I can view the services of a company |  |  | IMPORTANT | Done | Visitor or client chooses services option and is directed to the page having services offered by all companies | none
For sprint 3, updates and design done by members (excluding additional user stories as they are written before):
Nader |  | . client registration backend controller validations .post reviews backend controller validations .changes (required attributes) in client model and calculating the age from date of birth .Post review view arrangements .fixing answer question error .client register view arrangements
Mahmoud |  | . Admin Home Page . Navigation bar updates to let admin go through his functionalities . backend validations . flash messages instead of alerts
Rokaya |  | .Added payment in services .view bookings .create event frontend validations
Daniel |  | . frontend validations for updating events .backend validations for updating events .arranging flow when in update events
Shady |  | . front end validations for update and post promotions . backend validations for update and post promotions .solve the pictureURL in posting promotions .arrange the message in promotion front end controller .arrange error message in front end update promotions .
Sondos |  | . frontend and backend documentation . arranging CSS in view events .arranging CSS in view services .arranging date format in view events
Ali |  | . backend validations for create the services . frontend validations for create the services . backend validations for update the services . frontend validations for utpdate the services
Mireille |  | . fully changing client profile view .arranged the favorite companies of a client (frontend + backend) . alerts instead of messages in updating profile
Syrine |  | . hashing the update and reset password of the admin . Arranging flow to add buttons to update password . Adding a link below logins to reset password when forgotten .Arranging the date format in viewing promotions as a visitor and client and arranging the view itself .when clicking on "eventatk", redirect on profile depending who is connected .removing buttons payment, add review and others when a business is logged in .Added functions client, business, admin in factory to set the restrictions in the navigation bar and other views .arrangements in the navigation bar
Nardine |  | . changes in the interface of company's reviews .changes in interface of th ecompany profile .companies viewed in a list are only the verified ones